## Sheet1
Contents | March | April |  |  |  |  | May |  |  |  | June |  |  |  | July | August
| Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 1 | Week 2 | Week 3 | Week 4
Review project proposal and gathering existing dataset | bar: March Week 4 to April Week 3
Annotate missing labels and clean dataset | bar: April Week 2 to April Week 4
Preprocess video, audio, and text data | bar: April Week 4 to May Week 2
Set up baseline deep learning model (CNN/RNN) | bar: May Week 2 to May Week 3
Train and validate baseline model | bar: May Week 3
Train, tune, and compare model performance | bar: May Week 4 to June Week 1
Search for CUE-Net, VideoMamba and Implement multimodal model | bar: June Week 1 to June Week 2
Evaluate models using test data | bar: June Week 1 to June Week 3
Prepare final report (methodology, analysis, results) | bar: June Week 4
Draf Dissertation Paper submission (9th July)
Finalise documentation, upload code to GitHub, submission | bar: July Week 1 to August Week 2
Reflective Essay(21st August) | bar: August Week 3
Dissertation paper(21st August) | bar: August Week 3
Video recording(21st August) | bar: August Week 3